## Slide 1
PI PROJECT CONTROL
Project Execution
& Control Process
A practical operating framework for direction, execution, reporting and closure.
1 Govern
2 Execute
3 Communicate
4 Close
For PI / PnR project teams

## Slide 2
01 BACKGROUND
Why control is needed
02
The recurring failures are caused by unclear project state and weak control gates.
Assumption reported as fact
Finding has no confidence label or evidence.
Trial mistaken as baseline
Version-of-record is not explicit.
Review skipped
Output is shared before required verification.
Communication left open
Action is done but decision or acceptance is missing.

## Slide 3
02 PRINCIPLES
Five operating principles
03
01
Label the state
Fact, preliminary finding, assumption, risk or decision.
02
Control the baseline
One official baseline per milestone and scope.
03
Review by risk
Review intensity follows communication and delivery risk.
04
Close the loop
Every issue, decision and delivery has a closure condition.
05
Keep one source of truth
Shared records—not personal notes—define project state.

## Slide 4
03 FRAMEWORK
Three-layer control framework
04
1
PROJECT GOVERNANCE
Direction • ownership • milestone • decision rights
2
EXECUTION CONTROL
Version • issue/risk • change • technical review
3
COMMUNICATION & CLOSURE
Reportable status • delivery • acceptance • archive
These controls run together throughout the project—they are not sequential phases.

## Slide 5
04 GOVERNANCE
Project governance: define and realign
05
MANDATORY DEFINITION
REQUIRED RECORD
CONTROL GATE
Scope and committed target
Project brief
Stakeholder + Lead confirm
Milestone and priority
Milestone plan
Commitment is feasible
Owner and reviewer
Responsibility matrix
No unowned deliverable
Acceptance criteria
Exit checklist
Success can be verified
Escalation criteria
Risk rule
Trigger and receiver are known
Change rule: any change affecting scope, milestone, baseline or acceptance criteria must be recorded and re-aligned.

## Slide 6
05 VERSION CONTROL
Execution version control
06
TYPE
PURPOSE
REGISTER?
LOCAL TRIAL
Personal debug; not shared as status
No
SHARED TRIAL
Used for comparison or technical review
Yes
OFFICIAL BASELINE
Version-of-record for a milestone/scope
Mandatory
PROMOTION TO OFFICIAL
Run complete • required checks passed • QoR reviewed • limitations recorded • reviewer verified • Lead approved
Minimum traceability: input + script/flow + constraint + database path + owner + date + result summary

## Slide 7
06 ISSUE / RISK
Issue and risk lifecycle
07
Open
→
Validating
→
Assigned
→
In progress
→
Pending verification
→
Closed
Observation
Not yet validated
Issue
Confirmed current impact
Risk
Potential future impact
Decision
Authorized direction/disposition
CLOSURE OPTIONS
Fixed & verified • workaround accepted • risk accepted • superseded • out of scope • not reproducible
Each record requires impact, severity, owner, action, due date and evidence.

## Slide 8
07 CHANGE CONTROL
Change and decision control
08
1
Raise
Describe proposed change and reason
2
Assess
Evaluate QoR, scope and schedule impact
3
Decide
Approve, reject or defer with owner
4
Apply
Update baseline, plan and affected records
5
Inform
Communicate effective version and action
A decision is not complete until the owner, effective baseline and follow-up actions are recorded.
Examples: shape update • new netlist/SDC • milestone shift • target change • accepted violation

## Slide 9
08 REPORTING
Reportable status classification
09
LABEL
DEFINITION
REPORT LANGUAGE
CONFIRMED FACT
Evidence verified
“Based on Official B03…”
PRELIMINARY FINDING
Observation exists; analysis continues
“Current trial indicates…”
ASSUMPTION
Used temporarily without full evidence
“Assuming input remains…”
RISK
Potential impact has not occurred
“There is a risk to…”
PROPOSAL
Solution is not yet approved
“One option under review…”
DECISION
Authorized direction is confirmed
“Lead/RD agreed to…”
Every external status must include: classification + version/evidence + impact + action + owner + ETA.

## Slide 10
09 REVIEW GATES
Risk-based review and approval matrix
10
OUTPUT
OWNER
PEER / REVIEWER
LEAD
Local trial
Owner
—
—
Shared trial
Owner
Required
Lead informed
Internal working update
Owner
Optional
Spot-check
External / RD status
Owner
Required
Approve
Critical escalation
Owner + Peer
Support
Own communication
Official baseline / delivery
Owner
Verify
Approve
Lead controls the gates—not every execution step.

## Slide 11
10 DELIVERY & CLOSURE
Delivery and acceptance control
11
1
Ready
Package and checklist complete
2
Released
Version, path and receiver confirmed
3
Accepted
Accepted or accepted with conditions
4
Closed
Actions archived or reassigned
✓
Correct version and release path
✓
Required QoR/check reports
✓
Known limitations and waivers
✓
Open actions, owner and due date
✓
Receiver acknowledgement
NO RESPONSE?
Follow up within the agreed review window.
Escalate when acceptance blocks the milestone.
Do not silently treat no response as acceptance.

## Slide 12
11 OPERATING SYSTEM
Minimum project control system
12
One shared workbook or dashboard is the source of truth.
PROJECT SUMMARY
scope • milestone • owner • acceptance
VERSION REGISTER
shared trials • official baselines • changes
ISSUE / RISK / DECISION LOG
severity • action • owner • ETA • closure
DELIVERY / COMMITMENT LOG
release • acceptance • remaining actions
RULE
Update at the event—not only before the weekly report. Archive after milestone closure.

## Slide 13
12 ROLLOUT
Implementation rules
13
1
Define the source of truth
One shared location and owner.
2
Start with critical outputs
Official baselines, external reports and delivery.
3
Set review thresholds
Avoid Lead approval for low-risk work.
4
Review weekly
Check overdue issues, open decisions and commitments.
5
Improve after each milestone
Remove fields that do not support a decision.
A good process increases visibility without creating a reporting bottleneck.

## Slide 14
THE CONTROL PRINCIPLE
Clear state.
Controlled baseline.
Closed loop.
Lead responsibility
Make the project state
verified, traceable
and actionable.
Technical quality + control discipline = reliable execution